## Sheet1
PROJECT SCHEDULE: The Happiness Initiative
Assignment | Responsible Person | Work Dates | DUE Date | Complete? Y/N | Approval Deadline | Approved by: | Approve Date
Project Scope | JM, MA, TR, DG, CKN | 7/6-7/8 | 2011-07-08 | Y | 2011-07-15 | Laura M. | 2011-07-22
Project Schedule | JM | 7/6-7/8 | 2011-07-08 | Y | 2011-07-15 | NA | NA
Information Architecture | JM, DG, TR | 7/11-7/14 | 2011-07-13 | Y | 2011-07-15
Rework | JM | 7/22-7/24 | 2011-07-24
Finalized | JM |  | 2011-07-24
Branding (colors/logo) | CLIENT |  | 2011-07-22
Wireframes | JM, DG, TR | 7/15-7/20 | 2011-07-20 |  | 2011-07-22
Feedback due | CLIENT |  | 2011-07-22
Rework | JM | 7/22-7/24 | 2011-07-24
Finalized | JM |  | 2011-07-24
Visual Designs | JM, DG, TR | 7/22-7/29 | 2011-07-29 |  | 2011-07-29
Roughs | JM, DG, TR | 7/22-7/24 | 2011-07-27
Feedback due | CLIENT |  | 2011-07-28
Finalized | JM |  | 2011-07-29
Page Templates | DG, TR | 7/29-8/3 | 2011-08-03 |  | 2011-08-05
Design Specs | JM, DG, TR | 7/29-8/3 | 2011-08-03 |  | 2011-08-09
Development | MA, CKN | 8/5-8/12
Testing | MA, CKN | 8/13-8/15 | 2011-08-15
Hand-off Packet |  |  | 2011-08-17
Style | JM, DG, TR |  | 2011-08-17
Tech | MA, CKN |  | 2011-08-17
PRESENTATION | JM, MA, TR, DG, CKN |  | 2011-08-17
CLIENT MEETING 9:30AM at their office | JM, TR, DG |  | 2011-07-22 09:30 | Y | NA | NA | NA
** Assignment Responsibilities and dates are subject to change!